# 5.6 Financial Development Plan

The Financial Development Plan (FDP) links Baglung Municipality's fiscal capacity with the implementation of the Integrated Urban Development Plan for 2026-2041. In line with Nepal IUDP practice, the financial plan focuses on municipal income and expenditure, revenue improvement, resource mobilisation, cost sharing, private-sector participation, financial management of priority projects and the preparation of a rolling Multi-Sector Investment Plan (MSIP). It does not treat every public project as a commercial investment; detailed IRR/NPV appraisal is reserved for projects that later reach DPR/feasibility stage with verified demand, tariffs and operating costs.

## 5.6.1 Present Fiscal Condition and Financial Capacity

Baglung Municipality has a functioning local revenue base, but its ability to finance large IUDP investments independently remains limited. The approved FY 2083/84 budget is approximately NPR 114.95 crore. Of this, NPR 18.00 crore is reported as internal revenue and bank balance, NPR 15.55 crore as revenue sharing, NPR 78.22 crore as federal grants and NPR 3.17 crore as provincial grants. Internal revenue/bank balance plus revenue sharing therefore represents about 29.2% of the budget, while federal and provincial grants account for about 70.8%.

The FY 2082/83 budget was NPR 130.96 crore, with NPR 84.43 crore recurrent expenditure, NPR 44.22 crore capital expenditure and NPR 2.31 crore financial expenditure. Capital expenditure represented 33.8% of that year's total budget. The FY 2083/84 budget is about 12.2% lower than FY 2082/83, which demonstrates that a long-term IUDP cannot assume uninterrupted growth in intergovernmental transfers.

| Indicator | FY 2082/83 | FY 2083/84 | Planning interpretation |
| --- | --- | --- | --- |
| Total municipal budget | 130.96 | 114.95 | Budget contracted by about 12.2%; major projects require phasing and committed co-financing. |
| Internal source / internal revenue & bank balance | 14.79 | 18.00 | The labels are not strictly comparable because FY 2083/84 combines internal revenue with bank balance; recurring own-source revenue should be reported separately. |
| Revenue sharing | 16.13 | 15.55 | Important local/shared resource but externally determined and not equivalent to own-source revenue. |
| Federal grants | 91.35 | 78.22 | Largest financing source; creates exposure to federal budget changes. |
| Provincial grants | 3.19 | 3.17 | Small in the baseline but strategically important for co-financing sector projects. |
| Broad local/shared autonomy | 23.6%* | 29.2% | Useful monitoring indicator but should not be labelled pure own-source revenue. |
| Capital expenditure share | 33.8% | n/a | FY 2082/83 provides a reference point for long-term capital affordability, not a fixed future ratio. |

A second fiscal constraint is the Davgara Bus Park debt. The FY 2083/84 budget allocates NPR 3.50 crore for principal and interest payments to the Town Development Fund (TDF), equivalent to about 3.0% of the total municipal budget. Until the asset generates a stronger operating return, this fixed commitment reduces flexibility for new municipal capital expenditure. At the same time, NPR 6.40 crore is distributed through direct ward allocations and NPR 4.00 crore is retained as a municipal infrastructure pool. The IUDP should progressively combine such fragmented allocations where projects serve more than one ward or address strategic infrastructure gaps.

## 5.6.2 SWOT Analysis

| Strengths | Corresponding Opportunities |
| --- | --- |
| Existing local/shared revenue base and functioning municipal finance system. | Use GIS-based property mapping, business registration and digital billing to widen the effective tax base. |
| Strong commercial and banking activity in the Baglung Bazaar core. | Mobilise business taxes, service fees, municipal asset leases and co-financing with the private sector. |
| Digital/paperless governance and tax-payment incentives are already being introduced. | Build a transparent revenue dashboard and expand e-payment across municipal services. |
| Access to federal, provincial, TDF, NUGIP-type and other intergovernmental financing channels. | Use project preparation and matching funds to leverage larger infrastructure grants rather than relying only on municipal cash. |
| Tourism and agriculture projects create potential user-fee, lease and PPP revenue streams. | Structure concessions/cooperative operation so operating revenue supports O&M and reduces future municipal subsidy. |
| Weaknesses | Corresponding Threats |
| About 70.8% of the FY 2083/84 budget depends on federal and provincial grants. | Grant contraction or delayed releases can interrupt multi-year IUDP projects. |
| Davgara Bus Park carries a significant fixed TDF debt-service obligation. | Under-performing municipal assets can crowd out new development and maintenance expenditure. |
| Capital expenditure is fragmented across many small ward-level schemes. | Strategic utilities and multi-ward projects may remain underfunded while small projects accumulate. |
| Internal revenue and bank balance are combined in current reporting. | Weak distinction between recurring revenue and one-off balances can overstate sustainable fiscal capacity. |
| Exposure to landslides, floods and construction-cost escalation. | Emergency expenditure and cost overruns can displace planned capital spending. |

## 5.6.3 Problem Analysis

Core problem: Baglung Municipality has limited sustainable fiscal autonomy and fragmented investment capacity, making implementation of large, multi-year IUDP projects highly dependent on external financing and project-specific partnerships.

| Effects | Direct causes | Underlying causes |
| --- | --- | --- |
| Delay or scaling-down of strategic infrastructure; weak continuity of multi-year projects; insufficient O&M; high exposure to grant changes. | High grant dependence; fragmented ward capital; fixed debt-service burden; limited asset revenue; weak separation of recurring own-source revenue from one-off balances. | Incomplete property/business database; limited cost-recovery/asset management; project preparation gaps; annual-budget orientation; disaster and cost-escalation pressures. |

## 5.6.4 Objective Analysis

Desired future state: A fiscally sustainable, transparent and implementation-oriented municipal financing system that increases recurring local revenue, pools capital for strategic projects, leverages higher-government and private investment, and provides for operation and maintenance before assets are commissioned.

| Ends | Means |
| --- | --- |
| Greater continuity of IUDP projects; improved municipal service quality; lower exposure to grant shocks; stronger O&M and asset performance; increased local economic activity and municipal revenue. | GIS/digital revenue reform; business and property compliance; asset and bus-park revenue improvement; rolling MSIP and multi-year budgeting; project-preparation pipeline; PPP/cooperative financing; O&M ring-fencing and annual financial monitoring. |

## 5.6.5 Alternative Analysis

Four financing approaches were screened. The integrated approach is recommended because revenue reform alone does not finance major projects, while PPP/external finance alone does not solve weak municipal revenue, budget fragmentation or O&M management.

| Criteria | Alt-1 Current grant-led / fragmented | Alt-2 Revenue reform only | Alt-3 PPP / external finance only | Alt-4 Integrated FDP + MSIP |
| --- | --- | --- | --- | --- |
| Benefit to IUDP implementation | 1 | 2 | 2 | 3 |
| Fiscal sustainability | 1 | 3 | 2 | 3 |
| Revenue mobilisation | 1 | 3 | 2 | 3 |
| Investment leverage | 1 | 2 | 3 | 3 |
| O&M sustainability | 1 | 2 | 2 | 3 |
| Transparency / budget discipline | 1 | 3 | 2 | 3 |
| Resilience to grant shocks | 1 | 2 | 2 | 3 |
| Implementation simplicity | 3 | 2 | 2 | 2 |
| TOTAL SCORE (24) | 10 | 19 | 17 | 23 |

Alternative 4 - Integrated Financial Development Plan + MSIP - scores highest (23/24) and is adopted. It combines revenue improvement, capital pooling, project readiness, external/PPP leverage and O&M discipline rather than relying on one financing instrument.

## 5.6.6 Revenue, Resource and Expenditure Outlook

The IUDP plan period is fifteen years, so a single-year budget cannot be used as the investment ceiling. A scenario projection is used only for affordability testing. It begins from the FY 2083/84 gross budget of NPR 114.95 crore and applies 3%, 5% and 7% annual nominal growth. These are planning scenarios rather than guaranteed forecasts of transfers or own-source revenue.

| Scenario | Nominal annual growth | Phase I (5 yrs) | Phase II (5 yrs) | Phase III (5 yrs) | 15-year cumulative |
| --- | --- | --- | --- | --- | --- |
| Conservative | 3% | 610.29 | 707.49 | 820.17 | 2137.95 |
| Base planning case | 5% | 635.17 | 810.66 | 1034.63 | 2480.46 |
| Higher-reform | 7% | 661.05 | 927.15 | 1300.38 | 2888.58 |

Figure 5.6.1. Indicative gross municipal resource outlook under three nominal-growth scenarios.

.

The current Baglung IUDP draft carries a working fifteen-year investment envelope of approximately NPR 1,040 crore, with an indicative financing structure of 25% municipal own funds, 55% federal/provincial transfers, 17% private/PPP capital and 3% development-partner finance. This envelope should remain a working figure until all sector BOQs and the final flagship-project list are consolidated.

An affordability check is nevertheless useful. Under the 5% base resource scenario, the fifteen-year gross municipal budget is approximately NPR 2,480 crore. The municipal plus federal/provincial portion of the current IUDP envelope is NPR 832 crore (80% of NPR 1,040 crore), equal to about 33.5% of the base-case gross budget. This is close to the 33.8% capital-expenditure share recorded in FY 2082/83. The overall public investment scale is therefore broadly plausible only if the assumed higher-government support is sustained and private/development-partner components are genuinely additional. The proposed 25% municipal contribution should be treated as a stretch ceiling rather than a guaranteed commitment because municipal own-source resources must also cover recurrent services, debt service and O&M.

## 5.6.7 Revenue Improvement Action Plan (RIAP)

| Action | Immediate / Phase I | Medium-term | Lead responsibility |
| --- | --- | --- | --- |
| Separate recurring own-source revenue from bank balance in reporting | Create audited revenue baseline and monthly target-vs-actual dashboard | Publish annual own-source, shared-revenue and one-off balance indicators separately | Finance / Revenue Section |
| GIS-based property and business revenue base | Link property parcels and registered businesses to taxpayer records in core wards first | Expand coverage municipality-wide and update annually | Revenue + GIS/ICT |
| Digital billing and payment | Expand e-payment, reminders and taxpayer account reconciliation | Integrate receipts with municipal MIS and budget reporting | Revenue + ICT |
| Business registration and compliance | Complete unregistered-business drive and simplify renewal | Risk-based compliance and arrears management | Revenue / Ward Offices / BCCI |
| Davgara Bus Park asset recovery | Enforce routing/terminal use and establish a separate operating account | Review tariffs, concession/management structure and asset-renewal reserve | Municipality / Transport operator |
| Municipal property and concession management | Prepare inventory of leasable municipal assets and standard lease/concession documents | Competitive leasing/PPP with performance monitoring | Executive / Legal / Finance |
| Tourism and service revenue | Use legally permitted parking, facility, lease and service fees where services are provided | Ring-fence a share of site revenue for O&M of tourism assets | Tourism / Finance |
| Project preparation and matching fund | Create annual DPR/feasibility pipeline and protect matching funds | Maintain a rolling project shelf for federal/provincial/DP windows | Planning / Finance / Infrastructure |

## 5.6.8 Financial Assessment of Priority IUDP Projects

The five final projects are assessed at IUDP/pre-feasibility level. The purpose is to establish a defensible planning cost, likely financing structure, municipal exposure, O&M/revenue logic and the change expected in the present development scenario. Project-level FIRR, NPV or payback are not calculated where verified annual demand, tariffs, operating costs and financing terms are unavailable.

| ID | Priority project | Planning cost | Financial / implementation assessment |
| --- | --- | --- | --- |
| P1 | Baglung Agro-Processing, Collection & Cold-Chain Centre | 33.00 | Largest productive investment. Develop modularly and operate through a PPP/cooperative-private model. Municipal role should focus on land/enabling infrastructure, approvals and co-financing. Storage/processing charges and product/service revenues should cover a substantial share of O&M. Final CAPEX depends on production catchment, equipment specification and DPR. |
| P2 | Bhakunde Homestay & One-Day/One-Night Tourism Route | 2.25 | Incremental community-tourism investment. Prioritise access, route packaging and upgrades to existing homestays before adding new capacity. Guest income remains with operators; municipal spending is mainly enabling infrastructure, visitor facilities and promotion. |
| P3 | Bhairabsthan Adventure & Pilgrimage Package | 4.50* | Provisional IUDP allowance only. Public finance should cover pilgrimage/public-realm and safety-enabling works; rafting/climbing operations should be licensed/concessioned to qualified operators. Final cost requires hydrology, geotechnical, safety and site studies. |
| P4 | Shaligram Museum, Meditation & Pilgrim Facilitation Hub | 6.00 | Mixed public/trust/private project. Entry/service fees, retreat charges, café/retail leases and events are intended primarily to support O&M rather than repay the full capital cost. The investment strengthens an existing demand-backed attraction and extends visitor dwell time. |
| P5 | Kalika-Malika-Panchakot Heritage & Spiritual Tourism Circuit | 5.50 | Public circuit investment in route/heritage infrastructure with local enterprise participation. Revenue is mainly indirect through visitor spending, leases/services and increased business activity. Separate eco-resort investment is private and is excluded from municipal CAPEX. |

### 5.6.8.1 Consolidated Flagship Investment Requirement

| Project | Public/mixed project cost | Separate private investment | Key cost-status note |
| --- | --- | --- | --- |
| P1 Agro-processing & cold chain | 33.00 | - | Planning envelope; modular implementation; DPR and equipment quotations required. |
| P2 Bhakunde homestay route | 2.25 | - | Concept estimate; upgrades should precede new 4-6 room capacity. |
| P3 Bhairabsthan adventure package | 4.50* | - | Provisional allowance pending technical studies. |
| P4 Shaligram hub | 6.00 | - | Final team planning estimate. |
| P5 Heritage/spiritual circuit | 5.50 | 15.00 (illustrative eco-resort) | Public circuit cost final team estimate; resort remains private/PPP opportunity. |
| TOTAL | 51.25 | 15.00 | Total investment mobilised if private resort proceeds: 66.25 crore. |

## 5.6.9 Logical Framework Analysis (LFA) of Financial Development Plan

| Level / Output | Objectively Verifiable Indicators (OVI) | Means of Verification (MoV) | Key assumptions |
| --- | --- | --- | --- |
| Goal: Fiscally sustainable implementation of the Baglung IUDP | Strategic IUDP projects financed and maintained without destabilising essential municipal services. | Annual municipal budget, audited accounts, MSIP review, project completion/O&M reports. | Intergovernmental fiscal system remains functional; municipality maintains budget discipline. |
| Purpose: Increase municipal capacity to mobilise, leverage and efficiently allocate financial resources | Broader local/shared revenue moves from 29.2% toward the IUDP 40% stretch direction; major projects have identified financing before procurement. | Revenue statements, annual budget, financing agreements, procurement plan. | Taxpayer compliance and political support for revenue reform. |
| Output 1: Revenue base and reporting strengthened | Recurring own-source revenue reported separately from bank balance; GIS/digital taxpayer registry progressively completed. | Revenue database, audit reports, GIS/MIS records. | ICT systems maintained; data sharing across wards. |
| Output 2: Capital budget aligned with MSIP | Annual budget contains an MSIP cross-reference, phase and funding status for major IUDP projects; unfunded major packages are not tendered. | Annual programme, MSIP update, procurement/funding register. | Sector sections coordinate through Planning and Finance. |
| Output 3: Municipal assets and debt managed | Davgara Bus Park has an operating revenue account and annual performance review; new borrowing is subject to debt-capacity assessment. | Asset accounts, TDF debt statement, annual audit. | Terminal routing and fee collection are enforceable. |
| Output 4: External/PPP/cooperative finance mobilised | Flagship projects secure co-financing/concession arrangements before major construction; municipal capital share remains limited to enabling/co-financing functions where appropriate. | Grant agreements, PPP/concession contracts, cooperative/private financing records. | Projects reach feasibility/DPR and attract viable operators. |
| Output 5: O&M and financial monitoring institutionalised | 100% of major commissioned IUDP assets have an assigned operator, O&M plan and identified annual funding source. | Handover files, O&M budgets, asset-management register. | User/lease/service revenue and municipal allocations are collected as planned. |

## 5.6.10 Plans and Programmes

| Programme | Key actions | Responsible agency | Timeframe / priority |
| --- | --- | --- | --- |
| Municipal Revenue Database & GIS Tax Programme | Separate recurring own-source revenue; GIS property/business register; digital billing and compliance tracking. | Finance/Revenue, GIS/ICT, Ward Offices | Phase I - High |
| Municipal Asset & Bus Park Revenue Programme | Asset inventory; terminal routing; tariff/lease review; separate operating accounts and renewal reserve. | Executive, Finance, Transport/Infrastructure | Phase I - High |
| Strategic Capital Pooling & MSIP Budgeting Programme | Pool multi-ward resources for strategic projects; protect matching funds; adopt rolling five-year capital pipeline. | Planning, Finance, Municipal Executive | Phase I onward - High |
| Project Preparation & Co-financing Facility | Prepare feasibility/DPR/BOQ packages; maintain project shelf; target federal, province, TDF and development-partner windows. | Planning, Infrastructure, Finance | Phase I-II - High |
| PPP / Cooperative Investment Programme | Standard concession/PPP documents; competitive operator selection; performance and risk-allocation clauses. | Executive, Legal, Finance, sector sections | Phase I-II - High |
| O&M and Asset Lifecycle Programme | Assign operator before handover; ring-fence user/lease revenue; annual maintenance and replacement planning. | Finance, Infrastructure, sector operators | All phases - High |
| Financial Monitoring & Annual MSIP Review | Quarterly revenue/capital-execution dashboard; annual cost/funding/readiness update; publish financing gap register. | Finance and Planning Section | Annual - High |

# 6. Multi-Sector Investment Plan (MSIP)

## 6.1 Purpose and Approach

The MSIP converts the IUDP into a phased investment programme. Following the approach used in other Nepal IUDPs, projects are linked to priority, timing, indicative cost, financing responsibility and implementation agency. The MSIP is a rolling programme rather than a fixed fifteen-year promise: project costs, funding commitments and readiness are updated annually, while the five-year pipeline is revised with the municipal budget and periodic-plan cycle.

Because the five flagship projects have been developed and costed at a clearer planning level than many remaining sector programmes, the table below provides the firmest current MSIP for those projects. The wider NPR 1,040 crore IUDP envelope remains a working cross-sector figure and should be reconciled with final PDP, SDP, EnDP, EDP and IDP cost tables before the final report is locked.

## 6.2 Priority Project Phasing

| ID | Project | Total | Phase I 2026-31 | Phase II 2031-36 | Phase III 2036-41 |
| --- | --- | --- | --- | --- | --- |
| P1 | Agro-processing & cold chain | 33.00 | 18.00 | 10.00 | 5.00 |
| P2 | Bhakunde homestay route | 2.25 | 0.75 | 1.00 | 0.50 |
| P3 | Bhairabsthan adventure* | 4.50 | 1.00 | 2.50 | 1.00 |
| P4 | Shaligram hub | 6.00 | 2.00 | 3.00 | 1.00 |
| P5 | Heritage & spiritual circuit | 5.50 | 1.20 | 3.30 | 1.00 |
|  | TOTAL PUBLIC/MIXED | 51.25 | 22.95 | 19.80 | 8.50 |
| P5a | Eco/wellness resort (private) | 15.00 | - | 15.00 | - |

## 6.3 Indicative Financing Structure for the Five Priority Projects

| Project | Municipality | Province | Federal / DP | Private / PPP / Coop. | Community / Trust | Total |
| --- | --- | --- | --- | --- | --- | --- |
| P1 Agro-processing | 3.30 | 8.25 | 9.90 | 11.55 | 0.00 | 33.00 |
| P2 Bhakunde homestay | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 2.25 |
| P3 Bhairabsthan | 0.67 | 1.13 | 1.35 | 0.90 | 0.45 | 4.50 |
| P4 Shaligram | 0.90 | 1.50 | 1.80 | 0.90 | 0.90 | 6.00 |
| P5 Heritage circuit | 0.83 | 1.38 | 1.93 | 0.81 | 0.55 | 5.50 |
| TOTAL | 6.15 | 12.71 | 15.43 | 14.61 | 2.35 | 51.25 |

## 6.4 Financing Framework for the Wider IUDP

| Financing source | Current IUDP working share | Equivalent at NPR 1,040 Cr | Use in the IUDP |
| --- | --- | --- | --- |
| Municipal own funds | 25% | 260.00 | Project preparation, matching contribution, local public goods, O&M and selected capital works. Treat as a stretch ceiling subject to annual fiscal capacity. |
| Federal + provincial transfers | 55% | 572.00 | Major roads, water/sanitation, social infrastructure, DRR, sector grants and strategic public facilities. |
| Private / PPP capital | 17% | 176.80 | Revenue-linked tourism, agro-processing, concessions, hospitality and commercial components. |
| Development partners | 3% | 31.20 | Technical assistance, climate/DRR, governance and catalytic infrastructure. |
| TOTAL | 100% | 1,040.00 | Working IUDP envelope pending final cross-sector cost consolidation. |

.

## 6.5 MSIP Implementation Rules

No major project should enter procurement without a confirmed funding source for the procurement package and a defined municipal matching obligation.

Planning-stage costs must be replaced by DPR/BOQ estimates before tender; the MSIP should record both the original planning estimate and the latest approved cost.

Projects with commercial operating components should identify the operator and tariff/lease/service model before construction is completed.

Each major asset must have an O&M responsibility, annual maintenance requirement and funding source before handover.

The municipality should maintain a financing-gap register showing approved cost, committed finance, unsecured balance and next funding window.

The MSIP should be reviewed annually and re-prioritised at least once every five years using project readiness, service gap, fiscal capacity and observed demand.

## 6.6 Financial Monitoring Indicators

| Indicator | Baseline / current position | Direction / target | Frequency |
| --- | --- | --- | --- |
| Broad local/shared revenue autonomy | 29.2% of FY 2083/84 budget | Move toward the IUDP 40% stretch direction while separately reporting pure recurring own-source revenue | Annual |
| Recurring own-source revenue reporting | Not cleanly separated from bank balance in current headline line | Separate audited recurring own-source, revenue sharing and one-off balances | Annual |
| External grant dependency | 70.8% in FY 2083/84 | Reduce gradually through local revenue and leveraged project finance; no assumption of elimination | Annual |
| Davgara Bus Park financial performance | NPR 3.50 Cr annual TDF debt-service allocation; operating revenue needs strengthening | Separate operating account, cost-recovery review and annual asset-performance report | Quarterly / annual |
| MSIP funding readiness | No consolidated rolling funding register | 100% of major procurement packages have identified/committed financing before tender | Before tender |
| Capital cost update | Planning-stage estimates | DPR/BOQ update before procurement and annual MSIP revision | Annual / pre-tender |
| O&M plan before commissioning | Not consistent across all assets | 100% of major IUDP assets | Before handover |
| Flagship private/PPP mobilisation | Project-specific planning assumptions | Track signed/committed private, cooperative and concession investment | Annual |

## 6.7 Conclusion

Baglung Municipality can implement the IUDP only through a blended financing strategy. Current fiscal conditions do not support financing the programme from municipal own resources alone: external grants remain dominant, debt service reduces discretionary space and annual budgets are volatile. The appropriate response is not to reduce the IUDP to small ward schemes, but to improve recurring revenue, pool strategic capital, prepare investment-ready projects and use provincial, federal, cooperative, private and development-partner financing according to project type.

The five final priority projects require approximately NPR 51.25 crore of public/mixed investment, plus a separate illustrative NPR 15 crore private eco-resort opportunity. Their municipal contribution can remain limited if the agro-processing and tourism projects are structured around co-financing, PPP/cooperative operation and trust/community participation. The MSIP should therefore function as the municipality's rolling bridge between the long-term IUDP and the annual budget: only projects with clear need, readiness, financing and O&M arrangements should move from plan to procurement.